## Issues
Ref No | Systems | Page | Paragraph | Issue Type | The zones for warehouse segregation are to be: | Date Identified | Identifier | Potential Impact | Owner | Countermeasures/Actions | Comments | Escalation Details | Resolution | Status
example |  | 10 | 2.2.1 | wrong info | Wrong financial year start - should be 1st January | 2015-06-01 | ZZZZ | 5 | EdenOne
1 | SAP B1 |  | Page 15 section 2 |  | Says Bibby interface is out of scope, but KFL would like to understand the cost of building the same interfaces as used with Boughey, these would be EDI messages with the same content as the Boughey message any mapping to the Bibby format would be done by iTIM. | 2016-11-08 | AJ |  |  |  | Simon Advises setting up 1 interface with iTim to cover any new 3PL touch points which will save licence costs in the future |  | KFL to discuss interface options with iTim. | Closed
2 | SAP B1 |  | Page 16 section 3.1 |  | Databases if DEV and Data are only available during the build phase how do we control any issues that require fix and ensure they are tested before being pushed into the testing / training environment. How do we organise training so that the training courses can be repeated multiple times | 2016-11-08 | AJ |  |  |  | Dev Validation database to be set-up to sit between DEV and UAT |  | CS 09/11: Included in blueprint | Closed
3 | SAP B1 |  | Page 21 section 5.2 |  | If we can bring across existing supplier / customers references we will be OK to use automatically generated numbers for new customers / suppliers | 2016-11-08 | AJ |  |  |  | Yes will load and retain existing numbers. |  |  | Closed
4 | SAP B1 |  | Page 26 Section 8.2.3 Page 28 Section 8.2.3,1 |  | Blueprint review confirmed that the rebate % could be applied to the CSN, any customers not requiring the rebate will be ignored when the report is printed rebates on materials sold to more than one customer, there are very few products that can be sold to more than one customer. We agreed that the percentage would be held on the material and the accrual manually adjusted if this circumstance occurs. Copy of the rebate report when creating the credit, due to the volume of invoices for customers, would you want this to copy to the credit. Jan can you confirm? | 2016-11-08 | AJ |  | KF to review in blueprint |  | Confirmed with Jan that the credit will be raised manually from a report and we will not include the detail of the invoices CS 23/11 : Report to be changed to be date driven and the copy/paste will be optional |  | CS 23/11: included additional details
5 | SAP B1 |  | Page 31 section 8.2.4 |  | Boughey message at the review session we agreed that the Boughey confirmation of despatch would be processed and would take the sales order to invoiced status. Val confirmed that the sales order should be left open if any line was not delivered in full. We requested that sending / receiving the Boughey messages via EDI be costed this would give us the option of working with Bibby and future proof any change in 3PL in the future. | 2016-11-08 | AJ | [5 empty] | CS 16/11: Correct, SO will remain open and closing will be manual process as described in section 8.2.8 | Closed
6 | SAP B1 |  | Page 36 section 8.2.8 |  | Technical list of all deliveries in a date range - the requirement is separate from material trace and we would not want to do a full trace each day. Closure of sales orders - admin task to be run using Boyum document manager, the closure is done by the customer service team. I am not clear what admin in Boyum consists of. | 2016-11-08 | AJ |  |  |  | Technical - to be used as an example for training Open sales orders to be closed using 2 step process. Give access to Boyum to customer services or write a report. More detail around Boyum Document Manager needed Option to close multiple docs from 'open docs' to be confirmed and included |  | CS 09/11: Included option to close docs using standard open item list and information on Boyum | Closed
7 | SAP B1 |  | Page 37 section 8.2.9 |  | Premier ASN sent at point of despatch? CofA can this be generated and sent when a despatch note is generated (either from Boughey message or when despatch is confirmed from Knighton? | 2016-11-08 | AJ |  |  |  | KF action: Example CofA document to be sent to ensure we can capture required data CS 22/11: Details sent but to confirm if Phase II |  | Confirmed phase 2, e-mail from Mike Sabini | Closed - Phase II
8 | SAP B1 |  | Page 41 section 8.2.13 |  | Customer returns - technical to confirm is stock is to be receipted as blocked or Q status | 2016-11-08 | AJ |  | KF to review in blueprint |  | CS: Blocked status CS 23/11: Additional whse for 3PL returns (quarantine whse)
9 | SAP B1 |  | Page 45 Section 8.2.16 |  | Credit note approval, if Helen inputs the credit she cannot approve it, this seems to be a one step approval same as for the service credit note | 2016-11-08 | AJ |  | KF to review blueprint |  | Jan and Robin to confirm if this is OK - PF do not support |  | Anyone in Finance and Customer services can raise a PO request but two of three people need to approve. The three are Jan, Robin and Helen. This ensure that whoever raised the request it is always approved by one other person. CS 23/11: Linked on line 46
10 | SAP B1 |  | Page 50 section 9.2 |  | Changes to an MRP order, does setting the PO to unapproved stop the order being sent to the supplier? I understand the approver is notified and that the order cannot be receipted but if sent to the supplier we have a commitment to take the stock. | 2016-11-08 | AJ |  |  |  | Stop the send - can be done |  | CS 09/11: Included details on changing the layout to have a draft watermark or print blank if order unapproved CS 24/11: duplicate | Closed
11 | SAP B1 |  | Page 51 section 9.2.3 |  | Quantity break pricing not referenced How to monitor prices due to expire? How will the system respond to having two contracts for a material (could be different suppliers or two contracts for the same supplier) | 2016-11-08 | AJ |  | KF to review blueprint |  | C to add quantity Can only have a single blanket agreement no overlap of dates. Simon to confirm qty based rules. will always use the default supplier. CS 22/11: see issue 76 for contract details CS 23/11: Validation on contract or special price for stock POs to prevent order being added. Ability to select a contract after MRP was run. |  | CS 09/11: added ref to special prices for volume groups (non-contract) CS 24/11: included details
12 | SAP B1 |  | Page 56 section 9.2.7 |  | Goods receipt - can we confirm the quantity received in a delivery and have the application (PDMX) calculate the number of pallet labels needed | 2016-11-08 | AJ |  |  |  | Check with Tom on Wednesday's call |  | AJ 22/11 It is in the PDMX blueprint | Closed
13 | SAP B1 |  | Page 57 section 9.2.8 |  | Are there specific reports for Goods received not invoiced and overdue deliveries | 2016-11-08 | AJ |  |  |  | Open items list is standard to show any GRNI. Date range can be used to look at over due deliveries |  | CS 09/11: included open item report details | Closed
14 | SAP B1 |  | Page 59 section 9.2.10 |  | Invoice match with a price or quantity variance, payment is blocked but I thought Jan did not want the value to hit the ledger. Will the invoice hit the ledger? | 2016-11-08 | AJ |  |  |  | Talk to Jan about the process, reverse out? Not ideal but can work with it providing the blocked payments can be reported easily to create a journal to reverse out |  | Duplicate | Closed
15 | SAP B1 |  | Page 59 section 9.2.10 |  | Confirmation of service being provided, Jan to confirm which option is to be adopted | 2016-11-08 | AJ |  | KF to review in blueprint |  | 22/11 Will use draft invoice and get approval to release the invoice for payment |  | CS 24/11: included in doc
16 | SAP B1 |  | Page 63 section 9.2.13 |  | Returns - is the process different if the invoice has been received and or payment made? Posting to the goods received not invoiced account? | 2016-11-08 | AJ |  |  |  | Can link to an invoice if invoice has been received. AJ 22/11 Looked at example and postings will balance out but not ideal |  |  | Closed
17 | SAP B1 |  | Page 67 section 9.3 |  | Approvals for stock POs and POS being generated from changed MRP requisitions | 2016-11-08 | AJ |  |  |  | KFL to confirm how approval process is to work AJ 22/11 Approval needed by one of three peopleAndrew, Diane or Martin |  |  | Closed (duplicate)
18 | SAP B1 |  | Page 70 section 11.2 |  | No serial numbers to be used - what functionality comes with serial control? | 2016-11-08 | AJ |  |  |  | PDMX query for matcons. secondary batch number possible solution AJ 22/11 Matcon solution does not use serial numbers OK as is |  |  | Closed
19 | SAP B1 |  | Page 71 section 11.2.1 |  | Jan to confirm the number of item groups required, | 2016-11-08 | AJ |  | Knighton |  | KFL to confirm along with appropriate accounts
20 | SAP B1 |  | Page 72 section 11.2.3 |  | Mel to confirm the process for item master creation. | 2016-11-08 | AJ |  | KF to review in blueprint |  | 2 possible options - data import or direct input with approval steps. KFL team tp confirm CS 23/11: data import or DTW |  | CS 16/11: Document on import data sent to KF CS 24/11: included DTW or import tool
21 | SAP B1 |  | Page 72 section 11.2.5 |  | What will show in MRP if there is more than one supplier of a material? | 2016-11-08 | AJ |  |  |  | Can see alternate suppliers and change on recommendation |  | CS 09/11: included details | Closed
22 | SAP B1 |  | Page 73 section 11.2.6 |  | KFL Need to confirm the number of warehouses and their setup - not sure 50 is needed. Do in transit warehouses need to be added. Need to define rules for setting up items by warehouse. | 2016-11-08 | AJ |  |  |  | Need review with PDMX AJ 22/11 Only warehouse query is on weigh up room, is this a separate warehiuse as for NPD or a location in production CS 23/11 :CS check weight up whse and stock transfer |  | CS 23/11: Weight up will be separate whse | Closed
23 | PDMX |  | Page 75 section 11.2.9 |  | Need more details on stock transfers to and from 3PL, use of in transit warehouses and process to manage over and under delivery | 2016-11-08 | AJ |  | PDMX |  | Talk to PDMX - intransit warehouse control AJ 22/11 Need to create a report of stock in transit OK to manage if the load reference is visible in the in transit warehouse records CS 23/11 : check with PDMX
24 | PDMX |  | Page 75 section 11.2.9 |  | NPD transfers - I think we agreed that the warehouse would part pick from pallets but not split bags, can we confirm the process? | 2016-11-08 | AJ |  | PDMX |  |  |  | CS 09/11: included details
25 | SAP B1 |  | Page 76 Section 11.3 |  | Will need planner code, Premier material, APO planned, material type (raw, pack, FG, int) | 2016-11-08 | AJ |  | EdenOne/APO |  | AJ 22/11 For APO interface will also need the number of minutes to make 1000 units on the standard line, an alternate line and the number of minutes to make 1000 units on the alternate line. CS 23/11: add details |  | CS 16/11: Details included CS 28/11 Include details after APO scope
26 | SAP B1 |  | Page 77 section 12.2 |  | Effectivity dates in a BOM - need to see more detail of BOM and routing | 2016-11-08 | AJ |  |  |  | looking at process based on forecast demand to account for effective dates. Can create additional fields if needed. |  |  | Closed
27 | SAP B1 |  | Page 77 section 12.2 |  | Management of phantom pallets, reversal of production bookings | 2016-11-08 | AJ |  | KF to review in blueprint |  | PDMX AJ 22/11 Cannot reverse book a pallet. Need a control process to stop the creation |  | CS 16/11: Discuss with Tom CS 23/11: included that reversal is not possible. | Closed
28 | SAP B1 |  | Page 78 section 13 |  | Data interfaces - need to prioritise: Boughey and EDI first Existing 3 APO interfaces - must be there for go live Sales orders Works order update Master data | 2016-11-08 | AJ |  |  |  | AJ 22/11 Blueprint underway with VV and PC, SC, RJ |  |  | Closed
29 | SAP B1 |  | Page 86 section 18.2.2 |  | We talked about bringing across open transactions such as GRNs, open purchase invoices and open sales and purchase orders. What transactions will be needed to ensure we no longer need to process in Syspro. Does data take on ensure things like aged debt will pick up and age invoices correctly | 2016-11-08 | AJ |  | KF to review in blueprint |  | Write queries to look at open transactions. |  | CS 23/11 | Review at go-live
30 | SAP B1 |  | section 7.1 |  | nominal code list and levels on the nominal code. Are there any levels which are simply sub headings and if so what are they? The levels go to 1 - 5, what do these mean exactly? | 2016-11-07 | JC |  | Knighton to sign off |  | Email provided to Jan AJ 22/11 Jan has confirmed final version will be with you 23/11
31 | SAP B1 |  | Page 5 Section 1 |  | Calendar shown is 2016 / 2017 - start up is in 2017 / 2018 | 2016-11-08 | AJ | [5 empty] | CS 16/11: included in blueprint config doc | Closed
32 | SAP B1 |  | page 21 |  | Folders TBC by customer KFL to confirm names to be used | 2016-11-08 | AJ |  | EdenOne |  | Full path if folders not on AWS
34 | SAP B1 |  | Section 8.3 |  | Section 8.3 - needs populating but I am not sure what with | 2016-11-08 | AJ |  | Knighton |  | Standard transaction codes available - Edenone to provide a list of codes to share with accounts for confirmation of any extra ones reqauired. |  | CS 16/11 : list sent
35 | SAP B1 |  |  |  | Add Print & Delivery for Non-EDI (exclude Premier) Delivery Notes + CofA | 2016-11-14 | VV | [5 empty] | CS 16/11: Dispatch notes are printed | Closed
36 | SAP B1 |  | Section 11.2.9 |  | C grade products |  | AJ |  |  |  | AJ 22/11 Included in B1 and PDMX scope |  | CS 16/11: included details on doc | Closed
37 | SAP B1 |  | Page 14 Section 3.3 |  | The FD has asked that we add a US Dollar currency in addition to the two currently in use. |  |  |  | KF to review in blueprint |  |  |  | CS 23/11: included in document
38 | SAP B1 |  | Page 18 Section 5.3 |  | The pick and pack remarks, do these link with PDMX - not sure how they link to RF based picking? |  |  |  | KF to review in blueprint |  | CS 23/11: Not required on the order but can be displayed on CR from BP remarks |  | CS 28/11: Remarks are visible on gun in PDMX
39 | SAP B1 |  | Page 24 Section 8.2.1 |  | Comments about using quotations for premier, not sure how this would work in terms of converting the quotation into an actual order. Would this create an order / load as despatched / invoiced. Has this question been addressed to Val? Val any comment? |  |  |  | KF to review in blueprint |  | Val:As customer services do not enter any prices would suggest this query is directed at the account manager Colin Wilding to see how they are going to proceed as the contracts are set up by account managers, not sure if they use quotations. AJ:The first query, I am not sure how the quotation would work for premier, the suggestion seems to be a method of overcoming the fact that an order line cannot be changed once a part delivery has been made. I was not sure if you had been in discussion about the issue and proposed solution. I think Edenone need to give us more details of the proposal. CS 23/11: SO to be used instead of SQ |  | CS 23/11: included the process for SO
40 | SAP B1 |  | Page 25 Section 8.2.2 |  | For a material there will be one time based contract / customer dates will not overlap. So for any customer only one contract will be valid at a given period. If an EDI order is received with no contract in place for a material, I think you should log the order but place it on hold. Val do you agree? |  |  |  | KF to review in blueprint |  | AJ: The second query was about what to do with an EDI order if there is no price available on one or more lines, my suggestion is that we accept the order but place it on hold until a price is created for the line. The other alternatives are to not create the order at all or to create the order without the unpriced line. What would you prefer to see? CS 23/11: Discuss with VV |  | CS 23/11: included details in doc
43 | SAP B1 |  | Page 31 Section 84.2.3. |  | I do not think we send an order confirmation to customers Val to confirm. |  |  |  | KF to review blueprint |  | Val:Currently an email confirming the order is sent to the customer based on customer contact and not the 'email' address in the system for the customer invoices etc. I understood that there was going to be a 'button/option' for us to send an automatic email if we chose. AJ: The third comment I assume you want the ability to send an order confirmation document, I had never been in a session where this came up as being a requirement. Do you need a pop up button or is it easier to flag the customer as needing a confirmation and automatically send when the order is a CS 23/11: P&D for order confirmation, automaically for approved orders or update |  | CS 28/11: included details of button for order confirmation, but the email should be triggered by the user and not automaticaly as could lead to several emails being sent
44 | SAP B1 |  | Page 35 |  | two points are covered: CofA I propose that we do include in the initial scope but can pick up as a future enhancement if required.Jon and Mike to confirm The Premier ASN, I think this has been covered in the interface scope, Mel and Vitor can you confirm? | [5 empty] | AJ 22/11 No CofA in Pahse 1 |  |  | Closed
45 | SAP B1 |  | Page 36 Section 8.2.6.1 |  | EDI invoices are only sent via iTim no PDF document is e-mailed. |  |  |  | KF to review blueprint |  | CS 23/11: non-EDI invoices are emailed |  | CS 24/11: included in doc
46 | SAP B1 |  | Page 39 Section 8.2.8 |  | I believe that anyone in the finance team or customer service team can raise a credit request, only the senior members of the finance team can approve (Jan, Helen +1) and two approvers must approve. Jan to confirm names of those who can raise a credit note and those who can approve. |  |  |  | KF to review blueprint |  | AJ 22/11 Finance: Helen Jennings Jan Batkin Jayne Clark Katja Deeds Lucy Cupit Matthew Davies Paul Gavin Customer services: Melissa Lees Susan Lowe Valerie Westerman
47 | SAP B1 |  | Page 43 Section 8.3 |  | we no longer require the B1 UP Button button as long as there is a wayof flagging that an order is held / unapproved and not sent at the point of entry. This is required for manually entered orders and EDI orders received that need to be forwarded to the 3PL. |  |  |  | KF to review blueprint |  | AJ 22/11 Can you confirm that an EDI order will be validated upon receipt as if manualy entered and any problem with minimum order quantity, price or credit limit will flag the order as not approved. CS 23/11: UDF - ASN message sent to Boughy etc to include in B1 button validation |  | CS 28/11: All EDI orders will be validated and set as unapproved if there is an issue with min order, prices, etc. When SO is approved the message will be sent to Boughey
48 | SAP B1 |  | Page 46 Section 9.1 |  | For stock purchase orders there should always be a purchase order. Jan can you confirm if this is also required for non stock items? |  |  |  | KF to review blueprint |  | AJ 22/11 Jan confirmed this is required. Invoices always need to match to a PO CS 23/11: B1UP validation for GRPO without PO and PDMX switch off functionality |  | CS 23/11: included details in doc
49 | SAP B1 |  | Page 47 Section 9.2 |  | the approval for a manually entered Purchase Order or for an order being created from a modified MRP suggestion should be that 1 of three people approve. Andrew, Diane or Martin. Diane is this sufficient cover we could add Jan or someone else from Finance. |  |  |  | KF to review blueprint |  | AJ 22/11 Confirmed approval as one of: Martin West Diane Durieux Andrew Dearnaley CS 23/11: EO to discuss |  | CS 24/11: included details in doc
50 | SAP B1 |  | PAge 48 Section 9.2.3 |  | Jack how much notice do you require of a contract that is about to expire and would there be a benefit in gicing an alert if a contract quantity is about to be exceeded. If we have more than one contract in place I suggest we place the requirements against the oldest contract first until it is fully used / expired. |  |  |  | KF to review blueprint |  | AJ 22/11 Jack confirmed "No formal notice required - a weekly report for me to run would suffice." I want it to alert the person trying to raise an order for a product when there is no live contract (ie no volume left/out of date) - it should physically block them from raising the order and ask them to contact procurement to arrange a new contract(this is the same process as per Premier SAP). |  | CS 24/11: included details in doc
51 | SAP B1 |  | Page 56 Section 9.2.6 |  | Jan to confirm the approach required to managing authorisation of non stock invoices, post the Goods Receipt or add the invoice as a draft. |  |  |  | EdenOne |  | AJ 22/11 Jan confirmed use the draft invoice |  |  | Closed
52 | SAP B1 |  | Page 63 Section 9.3 |  | Jan to confirm the tolerances for invoice matching qty and value tolerances |  |  |  | KF to review blueprint |  | AJ 22/11 Tolerance is any value less than £1, otherwise needs approval. If qty difference send to warehouse (Sophie and team leads) if price to Jack Ward CS 23/11: Draft invoice with alert rather than postings? |  | CS 24/11: included details in doc
53 | SAP B1 |  | Page 65 Section 10.2.3 |  | Jan to provide the Bank Transfer file format definition | [5 empty] | AJ 22/11 Jan confirmed bank transfers are manual not sure what is needed CS 23/11: manual process no file submitted |  |  | Closed
54 | SAP B1 |  | Page 66 section 11.2 |  | Matcon solution is proposed in PDMX - review in the PDMX scope. | [8 empty] | Closed
55 | SAP B1 |  | Page 67 section 11.2.1 |  | Item groups are required for Finished Goods, Intermediates, Raw Materials and Packaging Materials | [8 empty] | Closed
56 | SAP B1 |  | Page 67 section 11.2.3 |  | raw and packing material coding - Mel to confirm the numbering format. Assumed that Mikes proosal of linking the Finished Goods, intermediate, CGrade and weigh up will be adopted. |  |  |  | Knighton |  | AJ 22/11 Confirmed on interface call, Finished Goods will have a prefix of M and start with number range 20,000 Intermediates will have a prefix I and start with a number range 20,000. Numbers will be manually entered. Mel to confirm number ranges for Raw and packaging no constraints wilth premier number ranges as these are not used in ECC or APO CS 23/11: Mel to confirm (prefix R and P)
57 | SAP B1 |  | Page 68 11.2.3 |  | Mel to confirm the option for controlling material load - likely tp be DTW or load from excel. | [8 empty] | Closed
58 | SAP B1 |  | Page 69 11.2.6 |  | Weigh ups is not a 3PL, it is an area in production were small quantities of ingredients are weighed out to create an intermediate for addition to a process order. Not sure if this is a separate warehouse or a location within the production warehouse. Flagged separatly as we want to part pallet pick to stock transfer individual bags to the weigh up room rather than picking full pallets. | [8 empty] | Closed
59 | SAP B1 |  | Page 73 Section 11.2.10.3. |  | The NPD process is as described in the flow diagram - NPD raise a stock transfer request, Warehouse pick the required number of bags and deliver to the NPD warehouse (new pallet labels as a pallet is split), NPD confirm the receipt and write off the material when used. The final two boxes relating to returns to the warehouse will normally never be used as only full unopened bags / boxes can be returned, unless NPDs requirement has changed they will not rqeuest a return. | [5 empty] | AJ 22/11 No returns required, cannot nove back and add a bag back to a pallet |  |  | Closed
60 | SAP B1 |  | Page 73 Section 11.3 |  | Premier materials - defines if this is a Finished Goods material manufactured for premier - drives the premier live load process. Material type - I think this is covered by the Item Group as this defines Finished Goods, Intermediates, Raw material, or Packaging Material. Not sure what MSL Level is meant to be and we seem to have the premierflag defined twice. |  |  |  | KF to review blueprint |  | CS 23/11: Review field list, Material Type - Item Group |  | CS 24/11: remove duplicates and MSL
61 | SAP B1 |  | Page 83 section 18.2.1. |  | A material will have a preferred manufacturing line but alternate lines can be accomodated and these create separate production versions. Each resource / line can be manufactured on needs certain details to be provided such as the run rate on that line. In APO the optimiser will try and produce a plan based upo the preferred resource but if it cannot it will plan to make on an alternate resource. We can pick the detail up in the integration calls as it relates only to data that APO needs. |  |  |  | KF to review blueprint |  | AJ 22/11 Discussed on interface call on 22/11 CS 23/11: Alternative resource not BOM |  | CS 28/11: included in doc
62 | SAP B1 |  | Page 84 section 18.2.3 |  | Jan to provide an example payroll import spreadsheet. | [5 empty] | AJ 22/11 Examples provided on 22/11 |  | CS 23/11: can be done using copy paste based on the example provided (data manipulation required to match GL codes) | Closed
63 | SAP B1 |  | page 87 section 21 |  | Martin West is the project sponsor. | [7 empty] | 23/11 - included in doc | Closed
64 | SAP B1 |  | section 1.6 |  | the Forecast module should be referenced? I am not sure if it is a separate module | [7 empty] | CS: This is part of MRP but I have included in the document | Closed
65 | SAP B1 |  | In section 4.2 |  | the FD has requested that all Fix Assets including those at zero value be loaded. This includes all plant and machinery. I think we will need to complete via a data load as direct input is going to take too long. | [5 empty] | CS: It will be possible to import the fixed assets and there is a tool in SAP B1 for this but can I ask why it is necessary to bring them at zero value? Can we propose to do this as a post go-live task as this will not be impacting any of the ledgers and balances? If there is time within the project we can include the imports of these assets. CS 23/11: After go-live data load for 0 value |  |  | Closed
66 | SAP B1 |  | Section 8.2.4 |  | an you confirm that the manullly entered orders will be sent to the 3PL based upon the despatch warehouse selected. Currently this is based upon pressing a button to trigger the send to the 3PL but if the user forgets the order is not picked up and despatched. | [5 empty] | CS: Yes, it will take into account the warehouse entered. |  |  | Closed
67 | SAP B1 |  | Section 8.2.9 |  | the delivery note is always sent with a delivery from site (Live load to 3PL or customer delivery). If a direct customer delivery from Knighton can we also print a CofA (subject to us capturing the data required and creating the report). The Premier ASN is part of the interface scope but needs to be triggered when a vehicle is despatched to premier and should match the delivery note. | [5 empty] | CS: OK. We need to see the details of the CofA to understand what information is required AJ 22/11 No CofA needed in this implementation CS 23/11: Check with PDMX - vehicle dispatch |  | Issue Raised on PDMX | Closed
68 | SAP B1 |  | Section 8.2.10 |  | "The process of sending sales invoices will be documented in the PDMX blueprint.", I will check but do not remember seeing anything about invoice generation in PDMX. This is the next document on my reading list. |  |  |  | Knighton |  | CS: I think there is a gap on this so we’ll make the necessary updates to the document
69 | SAP B1 |  | 6. 11.2.3 |  | the item number coding for Finished Goods and Intermediates will be managed outside of B1, we will not generate a workflow but have not determined if we will use the wizard or load from excel. Do you need a decsion for the scope? | [5 empty] | CS: Yes, correct. I only updated the blueprint configuration with the details discussed yesterday, but will include in the blueprint document. It will have an impact on the build if we require to do this in the system as we’ll need to have the validations, authorisations built. If it’s loading from excel with DTW or the import tool it will be more around training. |  |  | Closed
70 | SAP B1 |  | 11.2.6 |  | the new warehouse is for weigh ups, | [5 empty] | CS: OK |  |  | Closed
71 | SAP B1 |  | 11.2.9 |  | Can we reference that a simliar process will be used for the weigh up room. They only difference is that the stock in the weigh up warehouse will be consumed to a process order not written off. | [5 empty] | CS: Is this relating to the C grade items? AJ 22/11 No weigh ups are a specific form of intermediate, small quantities of materials weighed out for addition to a mix. |  |  | Closed
72 | SAP B1 |  | Section 13 |  | we discussed how to import a payroll journal from Equator, this does not need to be via an interface but can we upload a journal from a spreadsheet? | [5 empty] | CS: Yes, it can be copied using Copy From Excel functionality or DTW depending on the details required to be imported and arranging the spreadsheet in the format accepted by DTW/SAP. |  | CS: I have updated the document and included in section 18.2.3 | Closed
73 | SAP B1 |  | 10. Section 18.2.1 |  | I am not sure where in B1 details on the production line(s) a material can manufactured on or on the run rate on that line are kept but these are needed by APO and must be captured in B1. Some materials can be manufactured on more than 1 line and alternate lines must be captured. | [5 empty] | CS: We’ll verify where we need to include the details |  |  | Closed
74 | SAP B1 |  | Section 9.1 |  | Configuration there is a new Bank account, I have requested details from Jan |  |  |  | KF to review blueprint |  | CS: OK, send us the information when you have it AJ 22/11 I have sent the details |  | CS 24/11: included in doc
75 | SAP B1 |  |  |  | Currency valuation can you explain how the revaluation works and the impact of using the document date or the posting date. What would happen if we accidently post a document with a future date would it not be revalued until the future date is reached or will it revalue if it is in the balance sheet? | [5 empty] | CS: Revaluation is done by taking into account the posting date and it doesn’t look at future postings. |  |  | Closed
76 | SAP B1 |  |  |  | Multiple contracts I thin we have two types on contract: 1. Quantity based the contract is agreed for a fixed quantity and expires when the quantity is filfilled. 2. A time based contract the contract expires at the end date of the contract. The scenarios would be: 1. Quantity based (this assumes there is an end date on the contract which I think you said is standard): 1. The quantity has not been reached but the end date has been reached. 2. The quantity has been reached but the end date has not been reached. 3. The most recent MRP recommendation is for 200 and there is only 100 left on the contract. 4. The balance left on the contract is 100 but the minimum order quantity is 250. 5. We have MRP demand in the future that exceeds the contract quantity and goes beyond the contract end date - can we see demand in the future where no contract exists. | [5 empty] | Email sent on contract details |  |  | Closed
77 | SAP B1 |  | Page 7 / 2.1 |  | GLN number | 2016-11-18 |  |  | Knighton
78 | SAP B1 |  | Page 9 / 2.2 |  | Stock valuation method | 2016-11-18 |  |  | Knighton
79 | SAP B1 |  | Page 11 /2.2 |  | Tax Rate Determination: should be set to ‘Document Date’. | 2016-11-18 |  |  | KF to review blueprint |  |  |  | CS 28/11: Discussed with Jan and confirm doc date
80 | SAP B1 |  | Page 11 / 2.2 |  | Enable Extended Tax Determination is set to No. | 2016-11-18 |  |  | KF to review blueprint |  |  |  | CS 28/11: Discussed with Jan and set to Y
81 | SAP B1 |  |  |  | Fixed Assets Details | 2016-11-18 |  |  | Knighton
[5 empty] | COA | 2016-11-18 |  |  | Knighton
[5 empty] | GL Determination | 2016-11-18 |  |  | Knighton |  | CS 23/11: Section 7 blueprint configuration document
82 | SAP B1 |  | Page 57 / 10.9 |  | Additional shipping types required e.g. Ship from KF – ties in to Produmex. | 2016-11-18 |  |  | KF to review in blueprint |  | CS 23/11: One default shipping type with invoice option |  | CS 28/11: included in Configuration doc
83 | SAP B1 |  | Page 61 / 11.4 & 11.5 |  | Customer and Vendor Groups – will need a ‘Premier’ group for the interfaces, if possible, otherwise will need to create a UDF on the BP Master Data | 2016-11-18 |  |  | KF to review in blueprint |  | CS 23/11: KF to confirm groups(B2B, Retail, ATL, Out of Home, Other, Interm). Vendors (direct & indirect) CS 23/11: UDF for Premier codes on item codes |  | CS 23/11: Included details in doc
84 | SAP B1 |  | Page 10 |  | Intrastat - request Commodity codes, etc. and get report requirements | 2016-11-19 |  |  | Knighton |  | CS 23/11: KF to confirm intrastat details
85 | SAP B1 |  | Page 36 / 8.2.6.1 |  | Should EDI Invoices be excluded from the Print & Delivery run? | 2016-11-19 | [7 empty] | Closed
86 | SAP B1 |  | Page 40 / 8.2.7.3 |  | KFL to confirm if they only use 1 CHEP pallet type or they can have different one? | 2016-11-19 |  |  | Knighton |  | CS 23/11: KF (Mel) to confirm pallet type
87 | SAP B1 |  | Page 83 / 18.2.1 |  | KF to confirm if different resources or different versions of BOM | 2016-11-19 |  |  |  |  | AJ 22/11 Different resoure same BOM |  |  | Closed
88 | PDMX |  | Page 2 - |  | my contact number is 07428 404747 | [5 empty] | 29/11/2016: Changed in PDMX BP 4
89 | PDMX |  | Section 3 page 10, |  | Knighton are likely to use only handheld devices (subject to final confirmation from health and safety).
90 | PDMX |  | Section 4 page |  | The zones for warehouse segregation are to be: o MILK ALLERGENES  Organic (including fair trade-organic) Fair trade None of these o NON ALLERGENES  Organic (including fair trade-organic) Fair trade None of these o OTHER ALLERGENES  Organic (including fair trade-organic) Fair trade None of these o Geltin (bovine and porcine) |  |  |  |  | 29/11/2016: In previous recaps we discussed also HALAL as being a zone type. Is this not needed anymore?
91 | PDMX |  | Page 18 Section 5 |  | AP invoice will create a supplier debt?
92 | PDMX |  | Page 24 Section |  | 5.3.3 only selected materials will be receipted on quarantine status, the default should be available and overridden on the material master for selected materials. | [5 empty] | 29/11/2016: PDMX confirms. Was this an internal note for the KF team?
93 | PDMX |  | Page 25 Section 5.3.5 |  | The Premier way on managing the inbound materials is to flag a sustainable material on the material master and if it is being received into a factory there is reminder to booking in staff to complete and check the paperwork is as required. The popup asks 3 questions which have all to be answered in the affirmative or the goods cannot be received in. Materials will still be flagged to indicate the type of material and allergen they may contain, this will be pronted on the SSCC label. | [5 empty] | 29/11/2016: This is not a standard function on the handheld, if needed a CR can be made for this.
94 | PDMX |  | Page 42 section 6.1.8 |  | some products are managed to the day so will be an exact number of days, some by month which will calaculate the date and then move to the end of month. | [5 empty] | 29/11/2016 - PDMX: Changed in BP V4.0 that both calculations will work
95 | PDMX |  | Page 45 section 6.3.1 |  | The planning / MRP team will release an order, the production manager will start the order. We will have suggested orders for 104 weeks forward but the planners will only release orders covering a short term horizon (no more than a week). | [5 empty] | 29/11/2016: not a problem
96 | PDMX |  | Page 55 Section |  | 6.8 For premier Finished Goods products the label printed needs to indicate the destination location (Great Bear or Corby) based on the logic of fufilling the sales orders. | [5 empty] | 29/11/2016: added the label layouts and calculation of the depot# in the BP V4.0
97 | PDMX |  | Page 60 Section 6.10.1 |  | issuing more material to a process order, can you confirm that this will issue the material from the SSCC that is in the production line. Otherwise this is fine? | [5 empty] | 29/11/2016: in the screenshot you can see that the third column contains Batch1, Batch 2, BBD, SSCC. This column gives tells the user on which pallet the extra quantity will be consumed from
98 | PDMX |  | Page 61 Section 6.10.2 |  | returing material from a process order, if possible the return should be made to the last SSCC in the production area for that material. As this is the SSCC that is about to be returned to the warehouse. Ideally the process should be similar to 6.10.1 and part of the order closure, the requirement to adjsut the stock is always a result of the count of the stock to be returned to the warehouse, the system will propose we have a qty on an SSCC for return but the actual count is higher. | [5 empty] | 29/11/2016: Returning material will be without an SSCC. This means inventory will be posted on a bin location, with no SSCC linked to it. The inventory can be moved to the physical SSCC or to a new SSCC by using the handheld device. (Flow Ad hoc move)
99 | PDMX |  | Page 72 Section 7.2 |  | I am not sure what control there is to ensure that a load to Premier is always linked to a sales order for that delivery point. If an SSCC is scaned to a trailer how does PDMX that that that is a Corby delivery and check that each pallet added to that load has an open sales order for Corby. If more than one trailer is being loaded will it keep a rolling total of the open order quantity for the material / delivery point. | [5 empty] | 29/11/2016: This is been added as a requirement to the new workflow and described in the BP (section 7 - outbound)
100 | PDMX |  | Page 90 section 8, |  | we have proposed to follow a process similar to NPD for the weigh up room. The weigh up room will request part pallet movements and confirm receipt into a production warehouse location, the materials will be consumed to a process order (this will be instead of requesting picking).
101 | PDMX |  |  |  | when picking for production or to move to NPD / Weigh Up how can we ensure that part pallets are considered first within a batch FEFO sequence. For materials that are typically used in small quantities always moving a full pallet can result in multiple part pallets of the same batch which takes up more warehouse space. | [5 empty] | 29/11/2016: after further investigation it seems that the proposed setting on the picklist controller sometimes gives another result. Requested a CR to be 100 % that the system allocates always the smalles pallet quanities (ref CR-93)
102 | B1 |  |  |  | Can you confirm how we can manage stock under query with Boughey? E.g. Stock that is they are requesting be written off? Is there a status in B1 or do we need a separate warehouse | 2016-11-22 |  |  |  |  | 29/11/2016: need some more clariffication. Boughey is a non-PDMX warehouse. To see which batches are in the warehouse, the user can use the Batch transaction report in standard SAP B1 |  |  | Closed
103 | PDMX |  |  |  | Matcons
104 | PDMX |  |  |  | Vehicle inspection - outbound/inbound | [5 empty] | 29/11/2016: This is been added as a requirement to the new workflow and described in the BP (section 7 - outbound)
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
105 | PDMX |  |  |  | is there an option to override the pallets to pick for a sales order (controlled to specific users)?
106 | PDMX |  |  |  | UoM - bags, Kgs, cases, etc

## Master Data
Systems | Statuses | Identifiers | Owners | Potential Impact
SAP B1 | Open | EdenOne | EdenOne | 1
AddOn 1 | Customer Testing | Knighton | Knighton | 2
AddOn 2 | Closed | 3rd party | 3rd party | 3
4
5